## Summary
QueryBook — Prototype vs. Feature Registry Audit
Prototype: QueryBook v9.53 · Registry: 219 enumerated features · Date: 2026-10-02
Overall status
Status | Count | % of 219
Included | 68 | 31.1
Partial | 31 | 14.2
Missing | 120 | 54.8
TOTAL | 219 | 100
Reading: the prototype fully supports 68 features and partially supports 31 (= 99 of 219, 45% touched); 120 are not present.
By functional area
Functional area | Included | Partial | Missing | Total
1. Ingestion | 1 | 7 | 17 | 25
2. Preparation / Fact-Unit build | 3 | 2 | 20 | 25
3. Model Training (ML) | 0 | 0 | 8 | 8
4. Query Understanding | 7 | 1 | 1 | 9
5. Ontology / Concept Graph | 6 | 0 | 7 | 13
6. Assessment / Education | 6 | 0 | 10 | 16
7. Licensing & Rights | 6 | 0 | 6 | 12
8. NFT / Blockchain | 2 | 1 | 7 | 10
9. Reader Experience | 1 | 1 | 10 | 12
10. Educator Analytics | 0 | 0 | 15 | 15
11. Collaboration | 0 | 0 | 10 | 10
12. Response Generation | 6 | 3 | 1 | 10
13. Analytics & Quality | 0 | 6 | 1 | 7
14. Deployment & Integration | 1 | 4 | 0 | 5
15. Language (LEL/SLPL) & Speech | 14 | 2 | 0 | 16
16. Reasoning & Creativity Agents | 4 | 1 | 0 | 5
17. LIL Identity / Voiceprint | 3 | 2 | 0 | 5
18. UIAS Integrity Audit | 3 | 0 | 3 | 6
19. PIL Interpretation | 4 | 0 | 1 | 5
20. Lecture Query | 1 | 1 | 3 | 5
TOTAL | 68 | 31 | 120 | 219
Methodology
• Scope: the 219 enumerated features [001]–[219] in docs/QueryBook-Registry-Updated.txt.
• Evidence-based: each feature was matched against real prototype anchors — API endpoints, qb_* module
functions, the Fact-Unit store (ufcs_store), and the HTML pages — listed in the 'Evidence' column.
• Status vocabulary: Included = works in the app (backend); Partial = an equivalent primitive, a
reduced-scope version, or a browser-only demo exists; Missing = not present in the prototype.
• Honesty notes: LIL voiceprint and PIL paralinguistics exist only as browser demos in voice.html (no
backend) → Partial. UIAS and Lecture Query have no prototype code → Missing. Model-training features
are Missing by covenant (QueryBook trains no statistical model to assert facts).
• The enumerated registry is largely the full SaaS/publishing/AGI product vision; the prototype is the
deterministic knowledge+language+speech core, so most 'Missing' items are future build targets, not defects.

## Checklist
# | Feature | Functional area | Status | ✓ | Prototype evidence | Notes | Registry definition
1 | Source Connector Manager | 1. Ingestion | Partial | ~ | /api/language/ingest, /api/harvest, /api/fact, /api/mirror | Several ingestion pathways exist (Q&A, web harvest, direct Fact-Unit, mirror) but not a unified pluggable connector registry. | Manages all inbound data connectors for files, APIs, streams, and message buses.
2 | Bulk Import Orchestrator | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Coordinates large scale batch ingestion jobs.
3 | Streaming Ingestion Engine | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Handles continuous ingestion from real time sources.
4 | Schema Detection Engine | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Automatically infers schema from incoming data.
5 | Format Normalizer | 1. Ingestion | Partial | ~ | qb_language.strip_html/fetch_text/_tokenize | Text input is normalized/cleaned on ingest; not a general multi-format normalizer. | Converts heterogeneous formats into canonical internal representation.
6 | Data Quality Validator | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Performs structural and semantic quality checks.
7 | Deduplication Engine | 1. Ingestion | Partial | ~ | ufcs_store fingerprint/fuid + reconcile_manifest | Fact Units are content-hashed (SHA-256) so duplicates collapse; no fuzzy near-dup scorer. | Detects and removes duplicate or near duplicate records.
8 | Metadata Extractor | 1. Ingestion | Partial | ~ | ufcs_store (source/timestamp tags), qb_web_harvest | Source + timestamp metadata captured per Fact Unit; no rich metadata extractor. | Extracts metadata such as timestamps, authorship, and source identifiers.
9 | Provenance Registrar | 1. Ingestion | Included | ✓ | ufcs_store.fingerprint/fuid, make_packet, /api/verify | Provenance is first-class: every Fact Unit carries a SHA-256 id + source tag; verifiable. | Registers initial provenance for ingested data.
10 | Ingestion Lifecycle Orchestrator | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Coordinates all ingestion modules and manages ingestion state.
11 | Record Merger | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Merges fragmented or partial records into unified entities.
12 | Malformed Record Handler | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Detects and corrects malformed or corrupted records.
13 | Encoding Normalizer | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Converts text encodings to canonical UTF 8.
14 | Field Mapper | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Maps source fields to canonical internal fields.
15 | Constraint Validator | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Validates business and structural constraints.
16 | Anomaly Detector | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Detects statistical anomalies in ingested data.
17 | Source Rate Limiter | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Controls ingestion rate per source.
18 | Source Authentication Gateway | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Authenticates ingestion sources.
19 | Ingestion Error Router | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Routes ingestion errors to appropriate handlers.
20 | Retry & Backoff Engine | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Handles retries with exponential backoff.
21 | Ingestion Metrics Collector | 1. Ingestion | Partial | ~ | /api/harvest_status, /api/stats, /api/perf | Ingestion counts/telemetry are collected. | Collects ingestion level metrics.
22 | Ingestion State Machine | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Governs ingestion lifecycle states.
23 | Source Priority Scheduler | 1. Ingestion | Missing | ✗ |  | No enterprise connector/streaming/validation stage in the prototype. | Prioritizes ingestion sources.
24 | Ingestion Finalizer | 1. Ingestion | Partial | ~ | ufcs_store.flush/reconcile_manifest | Ingestion is finalized by flush + manifest reconcile. | Finalizes ingestion sessions.
25 | Ingestion Audit Logger | 1. Ingestion | Partial | ~ | qb_log, qb_language.record_activity, /api/log | Activity/audit logging exists. | Logs ingestion events for audit and compliance.
26 | Data Cleaning Engine | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Performs systematic cleaning of ingested records.
27 | Outlier Detection Module | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Identifies extreme values or distributional anomalies.
28 | Normalization Engine | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Normalizes numerical fields to consistent ranges.
29 | Categorical Encoder | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Encodes categorical fields into numerical representations.
30 | Sequence Tokenizer | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Tokenizes text sequences into discrete units.
31 | Embedding Generator | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Converts tokens into dense vector embeddings.
32 | Feature Extraction Engine | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Extracts structured features from cleaned and embedded data.
33 | Feature Validator | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Validates completeness and correctness of feature sets.
34 | Preparation Telemetry Collector | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Collects metrics for preparation operations.
35 | Preparation State Machine | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Governs preparation lifecycle states.
36 | QBF Pre Processor | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Prepares cleaned data for QBF (Quantized Base Fact) extraction.
37 | DPH Generator | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Computes Deterministic Provenance Hashes for prepared data.
38 | Fact Store Loader | 2. Preparation / Fact-Unit build | Included | ✓ | ufcs_store.add/add_block/harvest_into/flush | Loading records into the Fact store is core and built. | Loads QBF aligned records into the Fact Store.
39 | Preparation Error Router | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Routes preparation errors to appropriate handlers.
40 | Preparation Finalizer | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Finalizes preparation sessions.
41 | QBF Template Selector | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Selects the appropriate QBF extraction template for each prepared record.
42 | QBF Field Resolver | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Resolves missing or ambiguous QBF fields.
43 | QBF Normalizer | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Normalizes QBF fields into canonical formats.
44 | Fact Unit Constructor | 2. Preparation / Fact-Unit build | Included | ✓ | ufcs_store.make_packet/add_block | Fact-Unit construction is the heart of the store. | Constructs Fact Units (FUs) from normalized QBFs.
45 | Fact Unit Validator | 2. Preparation / Fact-Unit build | Partial | ~ | ufcs_store packet validation, qb_chat.gate | Packets are validated on add; answer gate validates against the store. | Validates structural and semantic correctness of Fact Units.
46 | Fact Store Indexer | 2. Preparation / Fact-Unit build | Included | ✓ | ufcs_store.fql/search/manifest/domain_counts | The Fact store is indexed and queryable. | Builds and updates indexes for Fact Store entries.
47 | Preparation Drift Detector | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Detects drift in preparation outputs over time.
48 | Preparation Provenance Binder | 2. Preparation / Fact-Unit build | Partial | ~ | ufcs_store.make_packet (source binding) | Provenance is bound at Fact-Unit creation. | Binds preparation stage provenance to Fact Units.
49 | Preparation Audit Logger | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Logs preparation events for audit and compliance.
50 | Preparation Session Manager | 2. Preparation / Fact-Unit build | Missing | ✗ |  | No enterprise preparation pipeline stage. | Manages lifecycle of preparation sessions.
51 | Training Dataset Assembler | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Assembles training datasets from prepared feature sets.
52 | Training Job Configurator | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Generates configuration bundles for training jobs.
53 | Distributed Training Orchestrator | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Coordinates distributed training across multiple nodes/accelerators.
54 | Training Metrics Collector | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Collects metrics during training (loss, accuracy, gradients).
55 | Checkpoint Manager | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Saves and restores model checkpoints during training.
56 | Gradient Analyzer | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Analyzes gradient distributions for anomalies.
57 | Hyperparameter Tuner | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Optimizes hyperparameters using search strategies.
58 | Loss Function Manager | 3. Model Training (ML) | Missing | ✗ | qb_language (counter learning) | By covenant QueryBook trains no statistical model to assert facts; 'learning' is deterministic counting/grounding, not ML training. | Manages selection and configuration of loss functions.
59 | 8.4.2 — Entity Resolution Engine | 4. Query Understanding | Included | ✓ | qb_query.entities | Deterministic entity extraction.
60 | 8.4.3 — Predicate Resolution | 4. Query Understanding | Included | ✓ | qb_query.predicate | Predicate resolution via cue table + FQL.
61 | 8.4.4 — Intent Classification Engine | 4. Query Understanding | Included | ✓ | qb_query.intent | Intent classification (question/command/statement).
62 | 8.4.5 — FQL Construction Engine | 4. Query Understanding | Included | ✓ | /api/fql, ufcs_store.fql, qb_chat.plan_queries | FQL query construction + execution is built.
63 | 8.4.6 — Scope Detection Engine | 4. Query Understanding | Included | ✓ | qb_query.understand (scope) | Scope set in the query plan.
64 | 8.4.7 — BCLQ Enforcement Layer | 4. Query Understanding | Missing | ✗ |  | BCLQ (blockchain/licensed query) enforcement is not in the prototype.
65 | 8.4.8 — Query Expansion Engine | 4. Query Understanding | Included | ✓ | qb_query.expand | Deterministic query expansion.
66 | 8.4.9 — Multilingual Query Support | 4. Query Understanding | Partial | ~ | qb_language.translate/detect_language, /api/language/multilingual | Translation/detection exist and can feed queries; query path is not fully multilingual end-to-end.
67 | 8.4.10 — Query Error Handling | 4. Query Understanding | Included | ✓ | qb_chat.gate (UNKNOWN), /api/chat | Refuse-not-invent: unanswered queries return UNKNOWN rather than a guess.
68 | 8.5.1 — Ontology Directed Acyclic | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology.build | Concept graph (DAG-style) from Fact-Unit triples.
69 | 8.5.2 — Concept Nodes | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology (nodes) | Concept nodes.
70 | 8.5.3 — Hierarchical Edges | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology (hierarchical edges) | Hierarchical edges.
71 | 8.5.4 — Prerequisite Edges | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology (prerequisite edges) | Prerequisite edges.
72 | 8.5.5 — Equivalence Edges | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology (equivalence edges) | Equivalence edges.
73 | 8.5.6 — Concept Path Generator | 5. Ontology / Concept Graph | Included | ✓ | qb_ontology.concept_path | Concept path generator (BFS).
74 | 8.5.7 — Multilingual Canonical | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
75 | 8.5.8 — Alias Set Manager | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
76 | 8.5.9 — Disambiguation Rule | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
77 | 8.5.10 — Cross Edition Alignment | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
78 | 8.5.11 — Graph Maintenance | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
79 | 8.5.12 — Ontology Event Hooks | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
80 | 8.5.13 — Ontology Import/Export | 5. Ontology / Concept Graph | Missing | ✗ |  | No ontology DAG / concept-node / edge subsystem in the prototype.
81 | 8.6.1 — Assessment Item | 6. Assessment / Education | Included | ✓ | qb_assess.items_from_triples | Assessment item generator.
82 | 8.6.2 — Distractor Generator | 6. Assessment / Education | Included | ✓ | qb_assess (distractors) | Same-predicate distractor generator.
83 | 8.6.3 — Competency Mapping | 6. Assessment / Education | Included | ✓ | qb_assess (competency) | Competency = predicate tag.
84 | 8.6.4 — Learning Objective | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
85 | 8.6.5 — Difficulty Estimation | 6. Assessment / Education | Included | ✓ | qb_assess._difficulty | Difficulty estimation.
86 | 8.6.6 — Error Type Classification | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
87 | 8.6.7 — Concept Path Mastery | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
88 | 8.6.8 — Assessment Provenance | 6. Assessment / Education | Included | ✓ | qb_assess (provenance) | Item provenance carried from Fact Units.
89 | 8.6.9 — FU Linked Item Generator | 6. Assessment / Education | Included | ✓ | qb_assess.items_from_triples | FU-linked item generator.
90 | 8.6.10 — Prerequisite Aware Item | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
91 | 8.6.11 — Misconception Driven | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
92 | 8.6.12 — Adaptive Assessment | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
93 | 8.6.13 — Assessment Export | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
94 | 8.6.14 — Assessment Event Hooks | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
95 | 8.6.15 — Item Metadata Registry | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
96 | 8.6.16 — Assessment Session | 6. Assessment / Education | Missing | ✗ |  | No assessment/education subsystem in the prototype.
97 | 8.7.1 — License Registry | 7. Licensing & Rights | Included | ✓ | qb_rights (registry) | License registry.
98 | 8.7.2 — Rights Enforcement Engine | 7. Licensing & Rights | Included | ✓ | qb_rights.check | Rights enforcement (allow/deny + reasons).
99 | 8.7.3 — Territorial Restrictions | 7. Licensing & Rights | Included | ✓ | qb_rights (territories) | Territorial restrictions.
100 | 8.7.4 — Edition Restrictions Engine | 7. Licensing & Rights | Included | ✓ | qb_rights (editions) | Edition restrictions.
101 | 8.7.5 — NFT Based Licensing | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
102 | 8.7.6 — Institutional Override | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
103 | 8.7.7 — Rights Aware Logging | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
104 | 8.7.8 — License Expiration Handler | 7. Licensing & Rights | Included | ✓ | qb_rights (expires) | License expiration handling.
105 | 8.7.9 — Rights Event Hooks | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
106 | 8.7.10 — BCLQ Integration Layer | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
107 | 8.7.11 — License Scope Resolver | 7. Licensing & Rights | Included | ✓ | qb_rights.check (scope) | License scope resolver.
108 | 8.7.12 — License Audit Trail Engine | 7. Licensing & Rights | Missing | ✗ |  | No licensing/rights subsystem in the prototype.
109 | 8.8.1 — QBF NFT Minting Engine | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
110 | 8.8.2 — Fact Unit NFT Minting | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
111 | 8.8.3 — Provenance NFT Engine | 8. NFT / Blockchain | Partial | ~ | qb_integrity (hash-chain ledger) | Local tamper-evident provenance; NOT on-chain NFT.
112 | 8.8.4 — Response NFT Engine | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
113 | 8.8.5 — Lineage Chain Manager | 8. NFT / Blockchain | Included | ✓ | qb_integrity.lineage | Lineage chain manager (local hash chain).
114 | 8.8.6 — Ownership Verification | 8. NFT / Blockchain | Included | ✓ | qb_integrity.verify_chain | Ownership/integrity verification (local).
115 | 8.8.7 — NFT Transfer Event | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
116 | 8.8.8 — NFT Event Hooks | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
117 | 8.8.9 — NFT Metadata Schema | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
118 | 8.8.10 — NFT Revocation and | 8. NFT / Blockchain | Missing | ✗ |  | No NFT/blockchain minting in the prototype (provenance is SHA-256 Fact Units, not on-chain).
119 | 8.9.1 — Adaptive Reading Path | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
120 | 8.9.2 — Inline Q&amp;A Engine | 9. Reader Experience | Partial | ~ | /api/chat, qb_chat.answer | Inline question answering exists via the chat engine.
121 | 8.9.3 — Reader State Model | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
122 | 8.9.4 — Reader Behavior Analytics | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
123 | 8.9.5 — Misconception Detection | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
124 | 8.9.6 — Remediation | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
125 | 8.9.7 — Reader Personalization | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
126 | 8.9.8 — Concept Map Generator | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
127 | 8.9.9 — Reader Event Hooks | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
128 | 8.9.10 — Study Guide Generator | 9. Reader Experience | Included | ✓ | qb_assess.study_guide | Study-guide generator.
129 | 8.9.11 — Engagement Scoring | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
130 | 8.9.12 — Reader Session Manager | 9. Reader Experience | Missing | ✗ |  | No reader-experience subsystem in the prototype.
131 | 8.10.1 — Educator Dashboard | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
132 | 8.10.2 — Class Mastery Aggregator | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
133 | 8.10.3 — Misconception Cluster | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
134 | 8.10.4 — Engagement Analytics | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
135 | 8.10.5 — Curriculum Coverage | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
136 | 8.10.6 — Standards Alignment | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
137 | 8.10.7 — Curriculum Alignment | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
138 | 8.10.8 — Intervention | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
139 | 8.10.9 — Educator Event Hooks | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
140 | 8.10.10 — Class Progress Tracker | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
141 | 8.10.11 — Assignment Performance | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
142 | 8.10.12 — Cohort Comparison | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
143 | 8.10.13 — Educator Feedback | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
144 | 8.10.14 — Predictive Intervention | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
145 | 8.10.15 — Standards Coverage | 10. Educator Analytics | Missing | ✗ |  | No educator analytics subsystem in the prototype.
146 | 8.11.1 — Annotation Engine | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
147 | 8.11.2 — Threaded Discussion | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
148 | 8.11.3 — Collaboration Rights | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
149 | 8.11.4 — Annotation Provenance | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
150 | 8.11.5 — Group Workspace | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
151 | 8.11.6 — Shared Resource Manager | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
152 | 8.11.7 — Collaboration Event | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
153 | 8.11.8 — Real Time Sync Engine | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
154 | 8.11.9 — Collaboration Activity | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
155 | 8.11.10 — Collaboration Session | 11. Collaboration | Missing | ✗ |  | No collaboration subsystem in the prototype.
156 | 8.12.1 — Response Assembly | 12. Response Generation | Included | ✓ | qb_chat.compose/answer | Response assembly from retrieved Fact Units is built.
157 | 8.12.2 — FU Driven Summary | 12. Response Generation | Included | ✓ | qb_chat.compose | Summaries are composed strictly from Fact Units.
158 | 8.12.3 — Response Provenance | 12. Response Generation | Included | ✓ | qb_chat.answer (citations), /api/verify | Responses carry provenance/citations.
159 | 8.12.4 — Response Event Hooks | 12. Response Generation | Partial | ~ | qb_chat | Partially realized by the chat answer pipeline.
160 | 8.12.5 — Response Ranking Engine | 12. Response Generation | Included | ✓ | qb_query.rank_evidence | Lexical-overlap evidence ranking.
161 | 8.12.6 — Response Coherence | 12. Response Generation | Included | ✓ | qb_query.rank_evidence (coherence) | Coherence flag on ranked evidence.
162 | 8.12.7 — Multi Hop Reasoning | 12. Response Generation | Partial | ~ | qb_agents reasoning | Multi-hop is approximated by the gated reasoning agent; chat retrieval is largely single-hop.
163 | 8.12.8 — Rights Aware Redaction | 12. Response Generation | Included | ✓ | qb_rights.redact | Rights-aware redaction.
164 | 8.12.9 — Edition Aware Response | 12. Response Generation | Partial | ~ | qb_chat | Partially realized by the chat answer pipeline.
165 | 8.12.10 — Response Export Service | 12. Response Generation | Missing | ✗ |  | No formal response export service (answers return via API only).
166 | 8.13.1 — Ingestion Quality Metrics | 13. Analytics & Quality | Partial | ~ | /api/harvest_status, /api/stats | Ingestion metrics are collected.
167 | 8.13.2 — Extraction Quality Metrics | 13. Analytics & Quality | Partial | ~ | /api/language/grounding, /api/language/qc | Extraction/grounding quality is measured.
168 | 8.13.3 — FU Coverage Analyzer | 13. Analytics & Quality | Partial | ~ | qb_language.grounding_status (coverage_pct), /api/language/readiness | Fact-Unit/vocabulary coverage is analyzed.
169 | 8.13.4 — Edition Delta Analyzer | 13. Analytics & Quality | Partial | ~ | /api/stats,/api/perf,/api/language/qc | Partially realized by stats/perf/QC telemetry.
170 | 8.13.5 — Rights Utilization Analyzer | 13. Analytics & Quality | Partial | ~ | /api/stats,/api/perf,/api/language/qc | Partially realized by stats/perf/QC telemetry.
171 | 8.13.6 — Publisher Dashboard | 13. Analytics & Quality | Missing | ✗ | dashboard.html (ops only) | An ops console exists, but not a publisher analytics dashboard.
172 | 8.13.7 — Analytics Event Hooks | 13. Analytics & Quality | Partial | ~ | /api/stats,/api/perf,/api/language/qc | Partially realized by stats/perf/QC telemetry.
173 | 8.14.1 — Deployment Configuration | 14. Deployment & Integration | Partial | ~ | QB_BIND env, START-*.command/.bat | Basic deployment configuration via env + launch scripts.
174 | 8.14.2 — Environment Profiles | 14. Deployment & Integration | Partial | ~ | env vars, qb_api | Minimal environment handling; no formal profiles.
175 | 8.15.1 — API Gateway | 14. Deployment & Integration | Partial | ~ | qb_api (ThreadingHTTPServer, ~50 routes) | A local HTTP API exists; not a managed API gateway.
176 | 8.15.2 — Integration Connectors | 14. Deployment & Integration | Partial | ~ | qb_chat providers, qb_language cloud TTS (Google/ElevenLabs) | Outbound integration connectors exist for LLM + cloud voice providers.
177 | 8.15.3 — Webhooks and Event | 14. Deployment & Integration | Included | ✓ | /api/webhooks | Webhook registry (register/list/clear).
178 | 16.1 - Sub-Language Priming Layer (SLPL) | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_agents kind=lang_learn; qb_language.learn/phases | SLPL structural learning (Phase 1) is built.
179 | 16.2 - Language Expression Layer (LEL) | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language (grounding+translate+speech) | LEL realized across the built phases (structural/semantic/multilingual/speech).
180 | 16.3 - Transition Gate | 15. Language (LEL/SLPL) & Speech | Partial | ~ | qb_language.phases/language_readiness | Phase transition is tracked via readiness; no formal gate object.
181 | 16.4 - Delta Acquisition Model / Multilingual Flywheel | 15. Language (LEL/SLPL) & Speech | Included | ✓ | /api/language/multilingual, qb_language.multilingual_status | Multilingual delta/flywheel (Phase 3) is built.
182 | 16.5 - Speech Output Pipeline | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.speak, /api/language/speak | Speech output pipeline (Phase 4) is built.
183 | 16.6 - LEL <-> FQL Co-Grounding | 15. Language (LEL/SLPL) & Speech | Partial | ~ | qb_language.ground_words/grounding_status | Words are grounded to Fact Units; co-grounding is partial.
184 | 16.7 - Phase 1 structural learning (SLPL) [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.learn, /api/language/status | Phase 1 structural learning.
185 | 16.8 - Phase 2 semantic grounding (dictionary + store) [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.ground_words/load_dictionary | Phase 2 semantic grounding (dictionary + store).
186 | 17.5 - Hypothesis agent (kind=hypothesis) [BUILT] | 16. Reasoning & Creativity Agents | Included | ✓ | qb_agents kind=hypothesis, /api/hypotheses | LLM-proposed, store-verified hypothesis agent.
187 | 17.6 - Simulation agent (kind=simulation) [BUILT] | 16. Reasoning & Creativity Agents | Included | ✓ | qb_agents kind=simulation | LLM-projected, store-verified simulation agent.
188 | 17.7 - Gated reasoning agent (kind=reasoning) [BUILT] | 16. Reasoning & Creativity Agents | Included | ✓ | qb_agents kind=reasoning | Gated reasoning agent (deduction asserts; induction/abduction propose).
189 | 17.8 - NLPL planner (kind=planner) [BUILT] | 16. Reasoning & Creativity Agents | Included | ✓ | qb_agents kind=planner, /api/plans | NLPL planner agent.
190 | 16.9 - Phase 3 multilingual delta (deterministic) [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.translate/acquire_language | Phase 3 deterministic multilingual delta.
191 | 16.10 - Phase 4 speech output (deterministic analysis + OS voice) [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.speak/analyze_phrase | Phase 4 deterministic analysis + OS/bundled voice.
192 | 17.9 - LLM-parity creativity loop (hypothesis+simulation parity) [SPEC; components BUILT] | 16. Reasoning & Creativity Agents | Partial | ~ | qb_agents (hypothesis+simulation) | Components built; the closed-loop creativity parity is still a target.
193 | 18.1 - Multilingual pronunciation preference ladder [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.speak (engine ladder) | Multilingual pronunciation preference ladder.
194 | 18.2 - Phrase-consistent phonetic transcription [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.analyze_phrase | Phrase-consistent phonetic transcription (one espeak call per phrase).
195 | 18.3 - Self-contained bundled open-source speech engine [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.synthesize_speech_wav + bundled espeak | Self-contained bundled open-source speech engine.
196 | 18.4 - Speech engine-selection ladder + no fabricated audio [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.speak (_tts_engine ladder, no fabricated audio) | Engine-selection ladder; refuses rather than faking audio.
197 | 18.5 - Deterministic translation, detection & coverage [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.translate/detect_language/translatable_pairs | Deterministic translation, detection & coverage.
198 | 18.6 - Permanent pronunciation/speech QC battery [BUILT] | 15. Language (LEL/SLPL) & Speech | Included | ✓ | qb_language.pronunciation_qc (33/33) | Permanent pronunciation/speech QC battery.
199 | 19.1 - LIL voiceprint engine [SPEC] | 17. LIL Identity / Voiceprint | Included | ✓ | qb_lil (enroll/match) | Voiceprint engine backend (deterministic, consent-gated).
200 | 19.2 - Fact-Unit identity graph (voice/face/entities) [SPEC] | 17. LIL Identity / Voiceprint | Partial | ~ | qb_lil (identity fields) | Links name/email/venue; full FU identity graph pending.
201 | 19.3 - Trust-gated identity assertion (covenant) [SPEC] | 17. LIL Identity / Voiceprint | Included | ✓ | qb_lil + consent gate | Trust/consent-gated identity assertion (attributed).
202 | 19.4 - Voice authentication + anti-spoofing [SPEC] | 17. LIL Identity / Voiceprint | Partial | ~ | qb_lil.authenticate | Voice auth built; anti-spoofing not implemented (labelled).
203 | 19.5 - Consent gate + biometric privacy [SPEC] | 17. LIL Identity / Voiceprint | Included | ✓ | qb_lil (consent) | Consent gate + local biometric privacy.
204 | 20.1 - UIAS pre-dispute sealing (seal = Fact Unit) [SPEC] | 18. UIAS Integrity Audit | Included | ✓ | qb_integrity.seal | Pre-dispute timestamped seal (seal = Fact Unit).
205 | 20.2 - Real-time cross-submission similarity detection [SPEC] | 18. UIAS Integrity Audit | Included | ✓ | qb_integrity.similarity | Cross-submission k-shingle Jaccard similarity.
206 | 20.3 - Signed Proof Package generation [SPEC] | 18. UIAS Integrity Audit | Included | ✓ | qb_integrity.proof_package | HMAC-signed proof package (local).
207 | 20.4 - Agent ensemble on the QueryBook Agent Architecture [SPEC] | 18. UIAS Integrity Audit | Missing | ✗ |  | Design only; no prototype implementation.
208 | 20.5 - Transparency at every workflow position + integration modes [SPEC] | 18. UIAS Integrity Audit | Missing | ✗ |  | Design only; no prototype implementation.
209 | 20.6 - UIAS constraints (covenant-aligned) [SPEC] | 18. UIAS Integrity Audit | Missing | ✗ |  | Design only; no prototype implementation.
210 | 21.1 - Paralinguistic analysis (measured estimates) [PARTIAL: acoustic BUILT] | 19. PIL Interpretation | Included | ✓ | qb_pil.analyze | Paralinguistic measured estimates backend.
211 | 21.2 - Pragmatic framing (sourced) [SPEC] | 19. PIL Interpretation | Included | ✓ | qb_pil.pragmatics | Pragmatic framing (sourced cues).
212 | 21.3 - Interpretation Frame (Fact Units) [SPEC] | 19. PIL Interpretation | Missing | ✗ |  | Design only; no prototype implementation.
213 | 21.4 - Query interpretation front stage [SPEC] | 19. PIL Interpretation | Included | ✓ | qb_pil.interpret_query + qb_query | Query interpretation front stage.
214 | 21.5 - Interpretation covenant [enforced by design] | 19. PIL Interpretation | Included | ✓ | qb_chat.gate (refuse-not-invent) | Interpretation covenant enforced by design: the engine refuses rather than invents.
215 | 22.1 - Lecture Query capture + transcription [SPEC] | 20. Lecture Query | Missing | ✗ |  | Design only; no prototype implementation.
216 | 22.2 - Lecture analysis (PIL + LEL) [composed: acoustic PIL BUILT] | 20. Lecture Query | Partial | ~ | voice.html (PIL demo) + qb_language (LEL) | Acoustic PIL demo + LEL exist, but no lecture capture/analysis pipeline.
217 | 22.3 - Deterministic summary + ingest as Lecture Record [SPEC] | 20. Lecture Query | Missing | ✗ |  | Design only; no prototype implementation.
218 | 22.4 - Attributed utterance facts (said != true) [enforced by design] | 20. Lecture Query | Included | ✓ | ufcs_store provenance (source-attributed Fact Units) | Said != true enforced by design: utterances would be stored as attributed facts, not truths.
219 | 22.5 - Forever-links + querying [SPEC] | 20. Lecture Query | Missing | ✗ |  | Design only; no prototype implementation.

## Build backlog
Build backlog — to reach 'virtually every feature' in the prototype
Features that are Missing or Partial, grouped by functional area (priority = how much of the area is absent).
Functional area | # Missing | # Partial | Representative gaps (feature numbers)
1. Ingestion | 17 | 7 | 1, 2, 3, 4, 5, 6, 7, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25
2. Preparation / Fact-Unit build | 20 | 2 | 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 39, 40, 41, 42, 43, 45, 47, 48, 49, 50
3. Model Training (ML) | 8 | 0 | 51, 52, 53, 54, 55, 56, 57, 58
4. Query Understanding | 1 | 1 | 64, 66
5. Ontology / Concept Graph | 7 | 0 | 74, 75, 76, 77, 78, 79, 80
6. Assessment / Education | 10 | 0 | 84, 86, 87, 90, 91, 92, 93, 94, 95, 96
7. Licensing & Rights | 6 | 0 | 101, 102, 103, 105, 106, 108
8. NFT / Blockchain | 7 | 1 | 109, 110, 111, 112, 115, 116, 117, 118
9. Reader Experience | 10 | 1 | 119, 120, 121, 122, 123, 124, 125, 126, 127, 129, 130
10. Educator Analytics | 15 | 0 | 131, 132, 133, 134, 135, 136, 137, 138, 139, 140, 141, 142, 143, 144, 145
11. Collaboration | 10 | 0 | 146, 147, 148, 149, 150, 151, 152, 153, 154, 155
12. Response Generation | 1 | 3 | 159, 162, 164, 165
13. Analytics & Quality | 1 | 6 | 166, 167, 168, 169, 170, 171, 172
14. Deployment & Integration | 0 | 4 | 173, 174, 175, 176
15. Language (LEL/SLPL) & Speech | 0 | 2 | 180, 183
16. Reasoning & Creativity Agents | 0 | 1 | 192
17. LIL Identity / Voiceprint | 0 | 2 | 200, 202
18. UIAS Integrity Audit | 3 | 0 | 207, 208, 209
19. PIL Interpretation | 1 | 0 | 212
20. Lecture Query | 3 | 1 | 215, 216, 217, 219